## Sheet1
TRANSPARENCY ASSESSMENT
Name of the Project: Ramu 2 Hydroelectricity Project
Name of Organisation: Institute of Democracy and Economic Affairs
Date of Assessment (Start): October 2021
Date of Assessment (End): April 2022
Phases | Information | CoST IDS draft definition | Response | Link to information: | Score | Average Phase Score | Imran's comments
PROJECT PHASE
Project Identification | Project owner | Name of the sponsoring government department | Department for State Enterprises: Kumul Consolidated Holdings (KCH - a State-owned Enterprise, which is the State's holding corporation for its eqity in the non-extractive sector buisnesses, including the utility companies ) | https://www.kch.com.pg/publications/kch-2019-annual-review/(see page 13 of the Annual Report for 2019) | 5 | 5.6667 | Correct
| Sector, subsector | Develop a list of sectors relevant to country e.g. housing, transport, energy, water etc. | Sector: Energy and Electricity Infrastucture including renewable energy. Sub-sectors: Generation, Transmisssion, Distribution Supply, Ancilliary facilities including dam for hydropower, Gas transmission, Public Gas distriburtion, Gas and gas works | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Project name | Specify the project name | Ramu 2 Hydro Power Project | https://www.kch.com.pg/ramu-2-hydropower-project-to-boost-power-generation-duma/ | 5 |  | Correct
| Project Location | Briefly specify location of the project | The Project on the Ramu River located downstream of the existing Yonki hydroelectric complex in the Eastern Highlands Province of Papua New Guinea. | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf (see #2.2) | 6 |  | Correct
| Purpose | Specify the socio economic purpose of the project | It is expected to lift Yonki’s electricity capacity from the current 93MW (once all major refurbishment and upgrade works are completed) to 273MW, an expansion of 194% in scheme’s generation capacity. More significantly, Ramu 2 is expected to increase total electricity generation capacity in Papua New Guinea by 36% from a (purportedly low cost) renewable source (20% increase according to Flagon Bekker, the Managing Director of PNG Power Ltd until in 2021) The development of the Ramu 2 project is in line with the PNG Development Strategic Plan 2010-2030 which outlines the following priorities: increase household access to electricity from current 12% to 70% by 2030; provide a national grid to increase reliability of electricity supply across the country; provide a secure, renewable energy base for PNG development pathway; reduce energy costs through greater hydropower development; and deliver on the Government’s commitment to support mining and industrial developments within the Highlands and Momase regions. | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf https://www.kch.com.pg/publications/kch-2020-annual-review/ (see sections on critical project andPNG Power and its precarious financial situation) https://www.kch.com.pg/ramu-2-progress-update/ | 6 |  | Correct
| Project description | Concise description and details of the project | Ramu 2 is a major infrastructure project being managed by Kumul Consolidated Holdings (KCH). The project site is located downstream from the existing Yonki Dam and is capable of generating 180 megawatts (MW) of renewable energy. | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
Project Preparation | Project Scope (main output) | Main outputs from the project that are being taken forward into construction (type, quantity, unit) | The scope of the Ramu 2 project includes a new 471,000m3 storage facility; three 61MW turbines; 30kms of new project access roads; 7km underground headrace tunnel; powerstation; 12km of new 132kv transmission lines; and various other temporary works. | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf https://www.kch.com.pg/ramu-2-progress-update/ https://www.businessadvantagepng.com/ramu-2-will-be-a-nation-building-project-says-png-power-md/ | 6 | 3.1429 | Since the source publishes some official documents, shouldn't the score be a 5? Also suggest to change the provided link, as it is not working. The web page https://www.kch.com.pg/ramu-2-progress-update/ is there, but for some reason I can open it on google, but not on microsoft Edge..or I can open the KCH website on Micrsoft Edge and find it under News and Media, and search back through older entries... I've left your comments for the benefit of my colleagues, in case its something on my end.
| Environmental impact | Briefly describe the environmental impacts and mitigation measures for this project e.g. impacts on flora, auna & woodlands, areas of natural beauty, carbon emissions etc. and mitigation measures e.g. pollution control, low carbon solutions, sustainable timber etc. | The contents of the approved Environmental Impact Statement have not been made publicly available, althuogh summary information is available on the website of Golder Associates which was commissioned to prepare the Environment Plan, with Tanorama undertaking the Social Impact component | https://www.golder.com/project/assessing-the-environmental-and-social-impacts-of-a-hydropower-station-in-papua-new-guinea/ https://www.pngreport.com/energy/news/1408169/more-talks-needed-on-ramu-2-power | 2 |  | Correct
| Land and settlement impact | State the amount of land and property that was acquired for the project e.g. 25km2 land, and related impacts e.g. archaeological issues (moved saxon burial site), local/indigenous settlements (relocated 5 indigenous villages of 500 villagers each), impacts on local businesses e.g. (30 business properties purchased). | Information is not publicly available; reports in the media refer to 6 clans (n Eastern Highlands and Morobe provinces) having signed an agreement to provide 1000 ha. | https://www.pngreport.com/energy/news/1411184/land-deal-done-on-ramu-2-hydro | 2 |  | Correct
| Contact details | Postal and electronic address of the Project Owner | Kumul Consolidated Holdings (KCH) 3rd Floor, Harbourside West, Stanley Esplanade, PO Box 320, Port Moresby NCD Papua New Guinea Phone: (675) 321 2977 / (675) 309 6700 ¦ Fax: (675) 321 0192 Email: Ramu2project@kch.com.pg | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Funding sources | Name the funding organisation(s)/sources of funding | Consortium led by Shenzhen Energy Group, with China Hydro: For development and construction of the project as a PPP, with an interim Power Purchase Agreement with PNG Power Ltd, the State provider of powerto businesses and private consumers Kumul Consolidated Holdings : All the studies carried out prior to and during the procurement phase | https://www.thenational.com.pg/morobe-shares-in-ramu-2-blessings/#:~:text=The%20Ramu%202%20hydro-electricity%20project%20will%20benefit%20both,wants%20to%20start%20construction%20by%20March%20next%20year. | 2 |  | Correct
| Project Budget | Specify the projected costs/allocated budget for the project (currency and amount). The budget includes land / property acquisition, environmental mitigation measures, H&S provisions, client, consultant & contractor costs, VAT etc. | There is no Budget allocation as the project is modelled under the PPP arrangement, as specified in the EOI. Shenzhen Energy group will secure the finance and construct the project under a BOOT arrangement, with the ownership of the assets transferred to the State after 25 years. | https://postcourier.com.pg/ramu-2-set-flood-country-energy/ | 2 |  | Correct
| Project budget approval date | Date project budget was authorised | The project does not appear in the Budget Documents and there was no budget approval. The Expression of Interest from KCH invited companies to bid to become the project operators, which would finance and run the project, with a PPA to sell the power to PNG Power, under an agreement with an Asset Entity, which will own the project and in turn by owned by the State, provincial governments and customary landowning clans. The arrangements between the operating company and assets entity also seem to have been adjusted during negotiation of the agreement. | https://www.thenational.com.pg/morobe-shares-in-ramu-2-blessings/#:~:text=The%20Ramu%202%20hydro-electricity%20project%20will%20benefit%20both,wants%20to%20start%20construction%20by%20March%20next%20year.? | 2 |  | Correct
Project Completion | Project status (current) | The current stage of the project. Select from identification, preparation, construction, completion, completed or cancelled. | Selection of the consortium to develop the project was done in 2016. 65 proponents responded to the invite to bid on 29 February 2016, before the deadline of 2nd March 2016, with 7 submissions made. The 3 shorlisted bids, in order, were 1) a Daewoo/Hyundai consortium, 2) Sinohydro Corporation, and 3) Shenzhen Energy. The latter two proponents subsequently combined their proposals and were somehow selected. It is still awaiting the start of construction. A conditional PPA was signed with PPL in Februrary 2021, with expected initial Kina 200 million of funding expected for initial work. Latest update was in March, 2021, when the (former) PNG Power's Managing Director said: "We should be looking at financial close in the next three-to-four months. Then, construction will be starting fairly early on the ground. We will make a head start on it. We are looking, in around six or seven years, that the plant will be commissioned. It also depends on our resource investors … we need off-takers." (the most up-to-date information on a Government website seemsto be on the KCH website, with the 2020 Annual Review, briefly mentioning measures already taken and actions still pending. | https://www.kch.com.pg/publications/kch-2020-annual-review/ (see sections on critical project andPNG Power and its precarious financial situation) https://www.businessadvantagepng.com/ramu-2-will-be-a-nation-building-project-says-png-power-md/ https://www.pngbusinessnews.com/articles/2021/2/government-and-chinese-firm-sign-hydropower-project | 5 | 3.1667 | Correct
| Completion cost (projected) | State projected or actual completion cost (currency and amount) | US$ 939 million (around PNG Kina 3.0 Billion); this K3 billion figure is provided by the Minister, and repeated, but there's no documentation available detailing or verifying it. (US$ 902 mill - K3.2 billion, was specified in March 2021 in 'Business Advantage') | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf (the EOI specified the expected financing arrangements for the PPP, and requirements to provide details of capacity to secure funds) https://www.kch.com.pg/ramu-2-hydropower-project-to-boost-power-generation-duma/ https://www.businessadvantagepng.com/ramu-2-will-be-a-nation-building-project-says-png-power-md/ | 6 |  | Since the source publishes some official documents, shouldn't the score be a 5? Also suggest to change the provided link, as it is not working. The EOI is available online,but seemingly not readily accessible on all browsers. The reported figure, provided by the MInister of K 3 billion kina is available in the media; maybe we stick with 2. Since one of the sources you used is from the KCH website, I would suggest moving it up to a 6
| Completion date (projected) | State projected or actual completion date | Projected for completion in 2022 in 2016 but delayed to 2024 in 2019. Current status is not known. | https://postcourier.com.pg/ramu-2-set-flood-country-energy/ | 2 |  | Correct
| Scope at completion | Indicate projected or actual scope of project. Aim is to show if the completed project scope differs from the original project scope. Specify main outputs (type, quantity, unit) | Projected scope of project. The project includes a new 471,000m3 storage facility; three (3) 61MW turbines: 30 kms of new project access roads; 7 km underground headrace tunnel; power station; 12 km of new 132kv transmission lines and various other temporary works. An indicative scope of the scope of the project is shown in Diagram 1. Key elements of the indicative scope include but are not limited to: Infrastructure requirements: weir and head works infrastructure, Weir structure, Intake structure, Temporary coffer dams (as required), Waterways infrastructure, Low pressure headrace tunnel, Access adits (as required), Pressure shaft, Surge shaft, High pressure headrace tunnel, Powerhouse inlet manifold and Tailrace. Power Station Infrastructure: Concrete substructure including, transformer fire walls and plinths and station sump; Steelwork superstructure, including crane rails; Building services and fit-outs for control/electrical areas, administration, ablutions and workshops; Turbine inlet isolation valves; 3 x pelton style turbines; 3 x vertical shaft arrangement Generators; Black start Generator; Tail race stop logs and 415V. auxiliiary power system: Single overhead travelling crane; Drainage and dewatering including an integrated sump in the powerhouse foundations; Cooling water system; Station compressed air supply. Transmission infrastructure: 3 x Main Transformers at Ramu 2 powerhouse; 132kV connection of the Ramu 2 power house to the Ramu 2 switchyard; Ramu 2 switchyard; 132kV Transmission line to the Sing Sing switchyard -Construction and commissioning only - Asset will transfer to PPL at start of operations phase; Connection to the Sing switchyard; Control and Communication Systems; Modern control system; Communication systems (locally and externally) ;CCTV systems to meet operational requirements. Roads infrastructure: Northern Access Road (permanent road). Construction and commissioning only - Asset will transfer at start of operations phase; Southern Access Road (permanent road)- Construction and commissioning only-Asset will transfer at start of operations phase; Surge shaft access road (permanent road). Construction and commissioning only - Asset will transfer at start of operations phase; Temporary construction access roads (as required). Miscellaneous infrastructure/services: Construction of accommodation village, and site offices (as required for construction); Concrete batching plants, material stockpiles, laydown areas (as required for construction); Temporary water and power (as required for construction); Site security and safety infrastructure; Environmental monitoring infrastructure; Sewage Handling and/or treatment plants; Potable Water Supply, storage and reticulation; Fueling Facilities; Transportation and logistics to site and within the site; Waste Management and disposal. | https://www.kch.com.pg/ramu-2-progress-update/ https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Reasons for project changes | Summary of primary reasons for any changes in scope, time and cost | Delays in contracting and financing, to lead on to construction. Project is now 8 years since the feasibility study, but finalising the PPA with the PPP is not concluded (presumably on the basis of the requirement by the PPP for PNG Power Ltd to purchase all the power generated by Shenzhen, even when the demand has not been established yet, notably with major mining operators), so construction has not started. |  | 0 |  | Correct
| Reference to audit and evaluation reports | Reference to publicly available technical and financial audits | Not known. But some recent Media reports say cost has increased to US$2.6 billion (PNG Kina 6.5 billion) |  | 0 |  | Correct
Contract Phase | Procuring entity | Enter name of the organisation carrying out the procurement | Kumul Consolidated Holdings | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 | 3.4286 | Correct
| Procuring entity contact details | Postal and Electronic address | 3rd Floor, Harbour Side West, Stanley Esplanade, Port Moresby P.O. Box 320, Port Moresby Papua New Guinea Attention: Parkop Kurua Email: Ramu2project@kch.com.pg | https://www.kch.com.pg/expression-of-interest-ramu-2-hydroelectric-project-independent-power-producers-ipp/ | 5 |  | Correct
| Procurement process | Develop a list such as International Competitive Bidding, National Competitive Bidding, Donor Procurement Rules, Framework, Direct Award | KCH Competitive Bidding for all SOE’s in PNG. Follows International Competitive Bidding procedures. | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Contract type | Develop a list such as Design, Supervision, Design & Supervision, Design & Build, Construction | Design Build operate and finance. IPP Model and BOOT Arrangement | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Contract status (current) | Select from pre-award, active or closed | Active | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf https://www.kch.com.pg/ramu-2-hydropower-project-to-boost-power-generation-duma/ https://www.kch.com.pg/publications/kch-2020-annual-review/ | 5 |  | Correct
| Number of firms tendering | Number of firms who submit a tender | Seven (7) | https://postcourier.com.pg/ramu-2-set-flood-country-energy/ | 2 |  | Correct
| Cost estimate | Currency and amount of the original pre-tender estimate of the contract | US$ 939 million (around PNG Kina 3.0 Billion) | https://postcourier.com.pg/ramu-2-set-flood-country-energy/ | 2 |  | Correct
| Contract administration entity | Enter name of the organisation carrying out the contract administrative entity if different from the Procuring Entity | Kumul Consolidated Holdings (same entity) | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Contract title | The formal name of the contract | Ramu 2 Hydro Electricity project | https://www.kch.com.pg/wp-content/uploads/2019/03/Ramu-2-EOI-Document.pdf | 6 |  | Correct
| Contract firm(s) | Legal name of supplier | Shenzhen Energy Group Company Limited, formerly Shenzhen Energy Investment Company limited, in a consortium with SinoHydro | https://en.wikipedia.org/wiki/Shenzhen_Energy https://en.wikipedia.org/wiki/Sinohydro | 2 |  | Correct
| Contract price | Currency and price at contract award | Project has not yet been implemented. Not Available |  | 0 |  | Correct
| Contract scope of work | Main outputs from the contract e.g. detailed design, supervision, project management and or type, quantity, unit for construction | Project has not yet been implemented. Not Available |  | 0 |  | Correct
| Contract start date and duration | Enter dates and Number of weeks from contract start date to (anticipated) completion date | Originally from 2017 for completion in 2021. Then delayed to 2018 for completion in 2024. | https://www.power-technology.com/marketdata/ramu-2-papua-new-guinea/ | 2 |  | Correct
Implementation | Variation to contract price | Difference between the price at contract award and the current projected price | Project has not yet been implemented. Not Available |  | 0 | 0.33333 | Correct
| Escalation of contract price | Escalation to date of the price of materials, labour, equipment etc. due to fluctuations in inflation, currency etc. | Not known. But recent Media reports say cost has increased to US$2.6 billion (PNG Kina 6.5 billion) | The National Newspaper. Port Moresby. 19 February, 2021. “Project depends on low-cost power” https://www.thenational.com.pg/project-depends-on-low-cost-power-marape/#:~:text=February%2019%2C%202021%20The%20National%20National%20PRIME%20Minister,investment%20and%20nothing%20to%20do%20with%20the%20Government | 2 |  | Correct
| Variation to contract duration | Difference between original duration at contract award and the current projected duration in weeks. | Project has not yet been implemented. Not Available |  | 0 |  | Correct
| Variation to contract scope | Any changes between original scope at contract award and the current scope | Project has not yet been implemented. Not Available |  | 0 |  | Correct
| Reasons for price changes | Summary of reasons for primary changes (e.g. variations) that then lead to changes in contract price, major price fluctuations and accumulative increase or decrease in price. | Project has not yet been implemented. Not Available |  | 0 |  | Correct
| Reasons for scope & duration changes | Summary of reasons for primary changes (e.g. variations) that then lead to changes in the scope and duration. | Project has not yet been implemented. Not Available |  | 0 |  | Correct